## Template
Traceability Matrix Project: VitalNest Wellness Website Relaunch Date:
Requirement ID | Requirement Type | Requirement Description | Source / Stakeholder | Business Objective / Goal | Acceptance Criteria | Linked Functional / Non-Functional Requirement | Owner | Priority | Status | Verification Method | Related Risks | Comments / Notes
1 | Functional | The website catalog shall allow customers to filter products with many criteria like categories, price range, product ratings…etc. | Marketing Team | Increase user engagement and customer satisfaction by improving customer browsing experience | Users can filter product results. Products and filters align with data visible on dashboard | Personalized Dashboard (4) | Marketing Lead | High | In-progress | User Acceptance Testing (UAT) | Resistance to change | None
2 | Functional | The website shall feature a subscription service where customers can opt-in for recurring deliveries of high-demand products | CEO | Provide competitive edge by offering convenience. Enhance customer loyalty and engagement | Smooth functionality to sign up for, manage and cancel subscriptions | Personalized Dashboard (4) (View and manage subscriptions) | External Web Development Vendor | High | In-progress | User Acceptance Testing (UAT) | Overextending resources | Regular milestone reviews are being conducted
3 | Transitional | All customer information, order histories and product data shall be seamlessly migrated from the old to new platform without loss or downtime | IT Manager | Maintain customer data | All data accurately transferred and fully accessible on the new site | None | IT Manager | Medium | To-do | Data migration testing | Data breaches, data loss, operational disruptions, non-compliance to data laws | Adhere to strict data security guidelines
4 | Functional | The website shall feature a personalized dashboard where customer scan track orders, manage subscriptions and view past transactions | Customer Representative | Enhnace transparency and trust, increase user engagement and reduce friction | Information from product catalog and subscription service and synchronized and easy to navigate | Product Catalog and Subscription Service (1&2) | Customer Representative | High | To-do | User Acceptance Testing (UAT) | Integration challenges | Feedback from UAT is crucial for making adjusments before launch

## Instructions
Traceability Matrix Completion Instructions
Entry | Instruction | Example
Project Name | Mention the project or program name for context. | Secure Retail System Upgrade
Requirement ID | Assign a unique identifier to each requirement using sequential numbering. | 001
Requirement Type | Specify if the requirement is Functional or Non-Functional. | Functional
Requirement Description | Provide a clear, concise description of the requirement. | The system shall allow login through biometric authentication.
Source / Stakeholder | Identify where the requirement originated (e.g., stakeholder, workshop). | Operations Manager
Business Objective / Goal | Describe the business need or strategic objective supported by the requirement. | Improve security and user experience
Acceptance Criteria | Define the conditions under which the requirement will be accepted. | User logs in successfully via biometrics
Linked Functional / Non-Functional Requirement | List related or dependent requirements by referencing their IDs. | 003 (Performance)
Owner | Identify the person or team responsible for fulfilling the requirement. | IT Lead
Priority | Assign a priority level (e.g., High, Medium, Low). | High
Status | Track the progress (e.g., Not Started, In Progress, Blocked, Completed). | In Progress
Verification Method | Specify how the requirement will be verified (e.g., Testing, Inspection). | Testing
Related Risks | Identify risks associated with the requirement to assist in planning. | Security breaches
Comments / Notes | Capture additional information or ongoing discussions. | Biometric SDK vendor confirmed.

## Example
Traceability Matrix Project: Secure Retail System Upgrade Project Date: 1 June 20xx
Requirement ID | Requirement Type | Requirement Description | Source / Stakeholder | Business Objective / Goal | Acceptance Criteria | Linked Functional / Non-Functional Requirement | Owner | Priority | Status | Verification Method | Related Risks | Comments / Notes
001 | Functional | The system shall allow login through biometric authentication. | Operations Manager | Improve security and user experience | User logs in successfully via biometrics | 003 (Performance) | IT Lead | High | In Progress | Testing | Security breaches | Biometric SDK vendor confirmed.
002 | Non-Functional | The app must support real-time inventory updates. | Supply Chain Head | Enhance operational efficiency | Inventory updates reflect within 2 seconds. | N/A | Product Manager | Medium | Not Started | Prototype Testing | System performance issues | Dependency on third-party API.
003 | Non-Functional | Biometric login must respond within 1 second. | Operations Manager | Provide seamless user experience | Login completes within 1 second. | 001 (Functional) | IT Lead | High | Not Started | Performance Testing | Delay in login may affect user adoption | Performance to be reviewed by IT team.