## Plan
Stakeholder Engagement Plan Format
Name | Current State | Desired State | Strategy
Hunter | Leading | Leading | Continue to actively engage and communicate to keep motivation and support levels high
Jose | Neutral | Supportive | Sell the project and its benefits, organzational priority and value to gain support
Preeti | Unaware | Leading | Inform about the project as soon as possible, vision, overview and needed contribution. Set up communication channels and actively engage to ensure contribution
Sunny | Supportive | Leading | Inform about needed contribution, task requirements actively engage to ensure contribution and participation
Mariko | Resistant | Supportive | Find a common ground and convince about benefits of the project. Find key motivators to ensure support
Krishna | Unaware | Supportive | Inform about the project as soon as possible, vision, overview, value and Quality Control code.
Level of Commitment Designators | ROLE | DEFINED
| U | Unaware: Stakeholder is unaware of the project
| N | Neutral: Stakeholder has yet to determine level of support
| R | Resistant: Stakeholder does not support the project
| S | Supportive: Stakeholder agrees with the project
| L | Leading: Stakeholder is supportive and actively engaged in the project